## Sheet1
Building Numbers | Units per Building | Contract Price | Date Started | Date of Draw 1 pd | Invoice # | Amount of Draw # 1 | Date of Draw 2 pd | Invoice # | Amount of Draw #2 | Date Finished | Date of Final Payment | Invoice # | Amount of Final Payment | Extra Invoice # | Assoc. Repair Cost | Extra PD date | Total per Building | Running Total | Original Price per Building | Difference | Cash on hand | Loan
906941.83
10 | 6 | 55000 | 2013-11-13 | 2013-10-31 | 7358 | 13750 | 2013-11-30 | 7406 | 13750 | 2014-01-10 | 2013-12-30 | 7468 | 27500 | 7436, 7517, 7518, 7519 | 1182 | 2014-02-28 | 56182 | 56182 | 57730.68 | 1548.68 | 850759.83
11 | 6 | 55000 | 2013-12-10 | 2013-12-20 | 7513 | 13750 | 2013-12-30 | 7514 | 13750 | 2014-01-10 | 2014-01-06 | 7515 | 13750 | 7546, 7545 | 1775 | 2014-02-28 | 43025 | 99207 | 57730.68 | 14705.68 | 807734.83
7 | 4 | 40487 | 2014-02-26 | 2014-02-26 | 7687 | 10121.78 | 2014-03-18 | 7688 | 10121.78 | 2014-06-02 | 2014-05-09 | 7689 | 20243.56 | 8108 | 430 | 2014-06-17 | 40917.12 | 140124.12 | 38487.12 | -2430 | 766817.71
8 | 3 | 30365 | 2014-03-01 | 2014-03-11 | 7690 | 7591.34 | 2014-03-31 | 7691 | 7591.34 | 2014-06-03 | 2014-05-09 | 7692 | 15182.66 | 8109 | 430 | 2014-06-17 | 30795.34 | 170919.46 | 28865.34 | -1930 | 1036022.37 | 300000
9 | 4 | 40487 | 2014-03-18 | 2014-03-20 | 7693 | 10121.78 | 2014-04-04 | 7694 | 10121.78 | 2014-06-04 | 2014-05-09 | 7695 | 20243.56 | 8110 | 575 | 2014-06-17 | 41062.12 | 211981.58 | 38487.12 | -2575 | 994960.25
6 | 8 | 80960 | 2014-04-09 | 2014-04-10 | 7850 | 20240 | 2014-04-22 | 7851 | 20240 | 2014-07-04 | 2014-07-15 | 7852 | 40480 | 8107 | 2115 | 2014-06-17 | 83075 | 295056.58 | 76974.24 | -6100.76 | 911885.25
28 | 5 | 50600 | 2014-05-19 | 2014-06-12 | 7899 | 12650 | 2014-06-12 | 7901 | 12650 | 2014-09-11 | 2014-09-11 | 7902 | 25300 | 8216 | 1342 | 2014-07-15 | 51942 | 346998.58 | 48108.9 | -3833.1 | 859943.25
27 | 4 | 40480 | 2014-04-21 | 2014-05-09 | 7895 | 10120 | 2014-06-12 | 7897 | 10120 | 2014-09-11 | 2014-09-11 | 7898 | 20240 | 8111 | 2310 | 2014-07-15 | 42790 | 389788.58 | 38487.12 | -4302.88 | 817153.25
26 | 5 | 50600 | 2014-06-16 | 2014-07-15 | 8160 | 12650 | 2014-07-15 | 8161 | 12650 | 2014-09-11 | 2014-09-11 | 8162 | 25300 | 8527 | 3100 |  | 53700 | 443488.58 | 48108.9 | -5591.1 | 763453.25
25 | 5 | 50600 | 2014-05-27 | 2014-06-12 | 7892 | 12650 | 2014-07-15 | 7893 | 12650 | 2014-09-11 | 2014-09-11 | 7894 | 25300 | 8475 | 6050 | 1916-07-24 | 56650 | 500138.58 | 48108.9 | -8541.1 | 706803.25
3 | 7 | 70840 | 2014-07-09 | 2014-08-28 | 8340* | 17710 | 2014-08-28 | 8341 | 17710 | 2014-10-08 | 2014-10-16 | 8342 | 35420 | 8528 | 3650 |  | 74490 | 574628.58 | 67352.46 | -7137.54 | 632313.25
1 | 6 | 60720 | 2014-08-04 | 2014-08-06 | 8431 | 15180 | 2014-08-26 | 8432 | 15180 | 2014-10-08 | 2014-10-16 | 8433 | 30360 | 8569 | 2675 |  | 63395 | 638023.58 | 57730.68 | -5664.32 | 681308.4 | 112390.15
2 | 4 | 40480 | 2014-08-14 | 2014-08-26 | 8478 | 10120 | 2014-10-16 | 8479 | 10120 | 2014-10-08 | 2014-11-18 | 8480 | 20240 | 8534 | 2475 |  | 42955 | 680978.58 | 38487.12 | -4467.88 | 638353.4
4 | 6 | 60720 | 2014-08-15 | 2014-09-19 | 8597 | 15180 | 2014-10-16 | 8598 | 15180 | 2014-10-08 | 2014-11-18 | 8599 | 30360 | 8702 | 2155 |  | 62875 | 743853.58 | 57730.68 | -5144.32 | 575478.4
23 | 8 | 80960 | 2014-09-08 | 2014-10-16 | 8680 | 20240 | 2014-11-18 | 8681 | 20240 |  |  |  | 40480 |  |  |  | 80960 | 824813.58 | 76974.24 | -3985.76 | 494518.4
24 | 5 | 50600 | 2014-11-10 | 2014-11-18 | 8773 | 12650 |  |  | 12650 |  |  |  | 25300 |  |  |  | 50600 | 875413.58 | 48108.9 | -2491.1 | 443918.4
5 | 7 | 70840 |  |  |  | 17710 |  |  | 17710 |  |  |  | 35420 |  |  |  | 70840 | 946253.58 | 67352.46 | -3487.54 | 373078.4
19 | 4 | 40480 | [14 empty] | 0 | 946253.58 | 38487.12 | 38487.12 | 373078.4
18 | 8 | 80960 | [14 empty] | 0 | 946253.58 | 76974.24 | 76974.24 | 373078.4
16 | 6 | 60720 | [14 empty] | 0 | 946253.58 | 57730.68 | 57730.68 | 373078.4
15 | 6 | 60720 | [14 empty] | 0 | 946253.58 | 57730.68 | 57730.68 | 423078.4 | 50000
21 | 4 | 40480 | [14 empty] | 0 | 946253.58 | 38487.12 | 38487.12 | 423078.4
22 | 5 | 50600 | [14 empty] | 0 | 946253.58 | 48108.9 | 48108.9 | 423078.4
12 | 4 | 40480 | [14 empty] | 0 | 946253.58 | 38487.12 | 38487.12 | 423078.4
13 | 4 | 40480 | [14 empty] | 0 | 946253.58 | 38487.12 | 38487.12 | 423078.4
14 | 3 | 30360 | [14 empty] | 0 | 946253.58 | 28865.34 | 28865.34 | 423078.4
|  | 1375019 | Contract |  |  |  | Approved for Payment |  |  |  |  | 8340* | 12650 | Pd 7/15
137 * | 436 | 59732 | Extra | [9 empty] | 5060 | Pd 8/28/15
|  | 1434751 | Total |  |  |  | Upcoming Payments | [9 empty] | Total Cost | 946253.58 | 1318183.86 | 371930.28
Total Cash |  | 1369331.98
Monthly Cont |  | 0
Avail Line of Credit |  | 50000
Under Funded |  | 15419.02
Note on P11: Mike: Approved to pay 12/1
Note on P13: Mike: Approved 12/2
Note on P14: Mike: Approved 12/2
Note on P15: Mike: This invoice show a charge of $4005.00 with a credit of $1530.00 this is due to price negotiation between my self and Painting plus on the extras. Mike Tolley
Note on P16: Mike: Approved 12/2

## Sheet2
Building Numbers | Units per Building | Contract Price | Date Started | Date of Draw 1 pd | Invoice # | Amount of Draw # 1 | Date of Draw 2 pd | Invoice # | Amount of Draw #2 | Date Finished | Date of Final Payment | Invoice # | Amount of Final Payment | Extra Invoice # | Assoc. Repair Cost | Extra PD date | Total per Building | Running Total | Original Price per Building | Difference | Cash on hand | Loan
906941.83
10 | 6 | 55000 | 2013-11-13 | 2013-10-31 | 7358 | 13750 | 2013-11-30 | 7406 | 13750 | 2014-01-10 | 2013-12-30 | 7468 | 27500 | 7436, 7517, 7518, 7519 | 1182 |  | 56182 | 56182 | 57730.68 | 1548.68 | 850759.83
11 | 6 | 55000 | 2013-12-10 | 2013-12-20 | 7513 | 13750 | 2013-12-30 | 7514 | 13750 | 2014-01-10 | 2014-01-06 | 7515 | 13750 | 7546, 7545 | 1775 |  | 43025 | 99207 | 57730.68 | 14705.68 | 807734.83
7 | 4 | 40487 | 2014-02-26 | 2014-02-26 | 7687 | 10121.78 | 2014-03-18 | 7688 | 10121.78 | 2014-06-02 | 2014-05-09 | 7689 | 20243.56 | 8108 | 430 | 2014-06-17 | 40917.12 | 140124.12 | 38487.12 | -2430 | 766817.71
8 | 3 | 30365 | 2014-03-01 | 2014-03-11 | 7690 | 7591.34 | 2014-03-31 | 7691 | 7591.34 | 2014-06-03 | 2014-05-09 | 7692 | 15182.66 | 8109 | 430 | 2014-06-17 | 30795.34 | 170919.46 | 28865.34 | -1930 | 1036022.37 | 300000
9 | 4 | 40487 | 2014-03-18 | 2014-03-20 | 7693 | 10121.78 | 2014-04-04 | 7694 | 10121.78 | 2014-06-04 | 2014-05-09 | 7695 | 20243.56 | 8110 | 575 | 2014-06-17 | 41062.12 | 211981.58 | 38487.12 | -2575 | 994960.25
6 | 8 | 80960 | 2014-04-09 | 2014-04-10 | 7850 | 20240 | 2014-04-22 | 7851 | 20240 | 2014-07-04 | 2014-07-15 | 7852 | 40480 | 8107 | 2115 | 2014-06-17 | 83075 | 295056.58 | 76974.24 | -6100.76 | 911885.25
28 | 5 | 50600 | 2014-05-19 | 2014-06-12 | 7899 | 12650 | 2014-06-12 | 7901 | 12650 |  |  | 7902 | 25300 | 8216 | 1342 | 2014-07-15 | 51942 | 346998.58 | 48108.9 | -3833.1 | 859943.25
27 | 4 | 40480 | 2014-04-21 | 2014-05-09 | 7895 | 10120 | 2014-06-12 | 7897 | 10120 |  |  | 7898 | 20240 | 8111 | 2310 | 2014-07-15 | 42790 | 389788.58 | 38487.12 | -4302.88 | 817153.25
26 | 5 | 50600 | 2014-06-16 | 2014-07-15 | 8160 | 12650 | 2014-07-15 | 8161 | 12650 |  |  | 8162 | 25300 |  |  |  | 50600 | 440388.58 | 48108.9 | -2491.1 | 766553.25
25 | 5 | 50600 | 2014-05-27 | 2014-06-12 | 7892 | 12650 | 2014-07-15 | 7893 | 12650 |  |  | 7894 | 25300 | 8475 | 6050 | 1916-07-24 | 56650 | 497038.58 | 48108.9 | -8541.1 | 709903.25
3 | 7 | 70840 | 2014-07-09 |  | 8340* | 17710 |  | 8341 | 17710 |  |  | 8342 | 35420 | 8474 | 2575 |  | 73415 | 570453.58 | 67352.46 | -6062.54 | 636488.25
1 | 6 | 60720 | 2014-08-04 | 2014-08-06 | 8431 | 15180 | 2014-08-26 | 8432 | 15180 |  |  | 8433 | 30360 |  |  |  | 60720 | 631173.58 | 57730.68 | -2989.32 | 575768.25
2 | 4 | 40480 | 2014-08-14 | 2014-08-26 | 8478 | 10120 |  | 8479 | 10120 |  |  | 8480 | 20240 |  |  |  | 40480 | 671653.58 | 38487.12 | -1992.88 | 535288.25
4 | 6 | 60720 |  |  |  | 15180 |  |  | 15180 |  |  |  | 30360 |  |  |  | 60720 | 732373.58 | 57730.68 | -2989.32 | 474568.25
5 | 7 | 70840 |  |  |  | 17710 |  |  | 17710 |  |  |  | 35420 |  |  |  | 70840 | 803213.58 | 67352.46 | -3487.54 | 403728.25
23 | 8 | 80960 | [14 empty] | 0 | 803213.58 | 76974.24 | 76974.24 | 322768.25
24 | 5 | 50600 | [14 empty] | 0 | 803213.58 | 48108.9 | 48108.9 | 272168.25
19 | 4 | 40480 | [14 empty] | 0 | 803213.58 | 38487.12 | 38487.12 | 231688.25
18 | 8 | 80960 | [14 empty] | 0 | 803213.58 | 76974.24 | 76974.24 | 150728.25
16 | 6 | 60720 | [14 empty] | 0 | 803213.58 | 57730.68 | 57730.68 | 90008.25
15 | 6 | 60720 | [14 empty] | 0 | 803213.58 | 57730.68 | 57730.68 | 79288.25 | 50000
21 | 4 | 40480 | [14 empty] | 0 | 803213.58 | 38487.12 | 38487.12 | 38808.25
22 | 5 | 50600 | [14 empty] | 0 | 803213.58 | 48108.9 | 48108.9 | -11791.75
12 | 4 | 40480 | [14 empty] | 0 | 803213.58 | 38487.12 | 38487.12 | -52271.75
13 | 4 | 40480 | [14 empty] | 0 | 803213.58 | 38487.12 | 38487.12 | -92751.75
14 | 3 | 30360 | [14 empty] | 0 | 803213.58 | 28865.34 | 28865.34 | -123111.75